## Backlog
ID | Work Item Type | Title 1 | Title 2 | Title 3 | Title 4 | State | Area Path | Iteration Path | Assigned To | Tags | Description | Acceptance Criteria | Repro Steps | Parent
1001 | Epic | Enable customer self-service |  |  |  | In Progress | Contoso Field Service\Portal Team | Contoso Field Service |  | Portal | <div>When a customer needs a technician, they want to book and track jobs online so that they don't have to phone the service desk.</div> | <ul><li>Customers can book, track and cancel jobs online</li><li>Service desk call volume for bookings drops by 30%</li></ul>
1002 | Feature |  | Book a job online |  |  | In Progress | Contoso Field Service\Portal Team | Contoso Field Service |  | Portal | <div>When I need a repair, I want to book a technician online so that I can choose a time that suits me.</div> | <ul><li>Booking available 24/7</li><li>Booking creates a job in the scheduling system</li></ul> |  | 1001
1003 | Product Backlog Item |  |  | Submit a job booking |  | Committed | Contoso Field Service\Portal Team | Contoso Field Service\Sprint 14 | Priya Shah <priya.shah@contoso.com> |  | <div>When I have selected a service and time, I want to submit my booking so that a technician is scheduled.</div> | <ul><li>Booking saved with service, address and time slot</li><li>Job ID displayed on submit</li></ul> |  | 1002
1004 | Task |  |  |  | Build booking form | In Progress | Contoso Field Service\Portal Team | Contoso Field Service\Sprint 14 | Liam Chen <liam.chen@contoso.com> |  | <div>Build the booking form UI so that customers can enter job details.</div> |  |  | 1003
1005 | Task |  |  |  | Validate address via address API | To Do | Contoso Field Service\Portal Team | Contoso Field Service\Sprint 14 |  |  | <div>Validate the entered address against the address API so that technicians get correct locations.</div> |  |  | 1003
1006 | Product Backlog Item |  |  | Receive booking confirmation email |  | New | Contoso Field Service\Portal Team | Contoso Field Service\Sprint 15 |  |  | <div>When my booking is submitted, I want a confirmation email so that I have a record of the booking.</div> | <ul><li>Email sent within 5 minutes of booking</li><li>Email includes job ID, date and time slot</li></ul> |  | 1002
1007 | Bug |  |  | Date picker allows past dates |  | Approved | Contoso Field Service\Portal Team | Contoso Field Service\Sprint 14 |  | Defect | <div>Fix date picker validation so that customers can't book a past date.</div> |  | <ol><li>Open booking form</li><li>Select yesterday's date</li><li>Form accepts the date</li></ol> | 1002
1008 | Task |  |  |  | Add min-date validation to date picker | To Do | Contoso Field Service\Portal Team | Contoso Field Service\Sprint 14 |  |  | <div>Set minimum selectable date to today so that past dates are blocked.</div> |  |  | 1007
1009 | Feature |  | Track job status |  |  | New | Contoso Field Service\Portal Team | Contoso Field Service |  | Portal | <div>When I have a booked job, I want to see its status so that I know when the technician will arrive.</div> | <ul><li>Status visible for all open jobs</li></ul> |  | 1001
1010 | Product Backlog Item |  |  | View job status |  | New | Contoso Field Service\Portal Team | Contoso Field Service\Sprint 15 |  |  | <div>When I log in, I want to see the status of my open jobs so that I don't need to call.</div> | <ul><li>Shows Booked, Scheduled, En route, Completed</li></ul> |  | 1009
1011 | Product Backlog Item |  |  | SMS notifications |  | New | Contoso Field Service\Portal Team | Contoso Field Service | [5 empty] | 1009
1012 | Risk |  |  | SMS vendor contract not signed |  | Active | Contoso Field Service\Portal Team | Contoso Field Service |  |  | <div>Procurement has not signed the SMS gateway contract. SMS features can't go live without it.</div> |  |  | 1009
1020 | Epic | Modernise the data platform |  |  |  | In Progress | Contoso Field Service\Platform Team | Contoso Field Service |  | Platform | <div>Migrate the on-prem SQL Server to Azure SQL so that we reduce hosting cost and improve resilience.</div> | <ul><li>All portal data served from Azure SQL</li><li>On-prem server decommissioned</li></ul>
1021 | Feature |  | Migrate database to Azure SQL |  |  | In Progress | Contoso Field Service\Platform Team | Contoso Field Service |  | Platform | <div>Migrate the portal database to Azure SQL so that the portal runs on managed infrastructure.</div> | <ul><li>Schema and data migrated with zero data loss</li><li>Portal cut over with under 1 hour downtime</li></ul> |  | 1020
1022 | Product Backlog Item |  |  | Migrate reference data |  | Committed | Contoso Field Service\Platform Team | Contoso Field Service\Sprint 14 | Sam Okafor <sam.okafor@contoso.com> |  | <div>Migrate reference data tables to Azure SQL so that lookups work after cut-over.</div> | <ul><li>Row counts match source</li><li>Lookups return identical results</li></ul> |  | 1021
1023 | Task |  |  |  | Script reference data schema | Done | Contoso Field Service\Platform Team | Contoso Field Service\Sprint 14 | Sam Okafor <sam.okafor@contoso.com> |  | <div>Script the reference data schema so that it can be deployed repeatably.</div> |  |  | 1022
1024 | Task |  |  |  | Run data validation | To Do | Contoso Field Service\Platform Team | Contoso Field Service\Sprint 14 |  |  | <div>Run row-count and checksum validation so that data loss is detected.</div> |  |  | 1022
1025 | Product Backlog Item |  |  | Decommission on-prem database server |  | New | Contoso Field Service\Platform Team | Contoso Field Service |  |  | <div>Decommission the on-prem SQL server so that hosting costs stop.</div> | <ul><li>Server powered off</li><li>Backups archived</li></ul> |  | 1021
1026 | Feature |  | SSO |  |  | New | Contoso Field Service\Platform Team | Contoso Field Service | [5 empty] | 1020
1027 | Product Backlog Item |  |  | SSO stuff |  | New | Contoso Field Service\Platform Team | Contoso Field Service |  |  | <div>Need to do SSO</div> |  |  | 1026
1030 | Impediment | Test environment unavailable |  |  |  | Open | Contoso Field Service | Contoso Field Service\Sprint 14 |  | Blocker | <div>UAT environment is down after the network change so that testing can't proceed.</div>