## Upload preview
Change | ID | Work Item Type | Title 1 | Title 2 | Title 3 | Title 4 | State | Area Path | Iteration Path | Assigned To | Tags | Description | Acceptance Criteria | Repro Steps | History
CONTEXT | 1001 | Epic | Enable customer self-service |  |  |  | In Progress | Contoso Field Service\Portal Team | Contoso Field Service |  | Portal | When a customer needs a technician, they want to book and track jobs online so that they don't have to phone the service desk. | • Customers can book, track and cancel jobs online • Service desk call volume for bookings drops by 30%
CONTEXT | 1002 | Feature |  | Book a job online |  |  | In Progress | Contoso Field Service\Portal Team | Contoso Field Service |  | Portal | When I need a repair, I want to book a technician online so that I can choose a time that suits me. | • Booking available 24/7 • Booking creates a job in the scheduling system
UPDATED | 1003 | Product Backlog Item |  |  | Submit a job booking |  | Committed | Contoso Field Service\Portal Team | Contoso Field Service\Sprint 14 | Priya Shah <priya.shah@contoso.com> |  | When I have selected a service and time, I want to submit my booking so that a technician is scheduled. | • Booking saved with service, address and time slot • Job ID displayed on submit |  | 13/10/2026 stand-up: demo to business accepted. Reschedule requested as a separate PBI. Stays Committed until address validation is done.
UPDATED | 1004 | Task |  |  |  | Build booking form | Done | Contoso Field Service\Portal Team | Contoso Field Service\Sprint 14 | Liam Chen <liam.chen@contoso.com> |  | Build the booking form UI so that customers can enter job details. |  |  | 13/10/2026 stand-up: booking form finished and merged (Liam).
UPDATED | 1005 | Task |  |  |  | Validate address via address API | In Progress | Contoso Field Service\Portal Team | Contoso Field Service\Sprint 14 |  |  | Validate the entered address against the address API so that technicians get correct locations. |  |  | 13/10/2026 stand-up: address validation started. Blocked on vendor API key – see new impediment.
NEW |  | Impediment |  |  |  | Obtain address API key from vendor |  | Contoso Field Service\Portal Team | Contoso Field Service\Sprint 14 |  |  | Obtain the address API key from the vendor so that address validation can be built and tested. |  |  | Raised at 13/10/2026 stand-up. Aisha to chase vendor.
NEW |  | Product Backlog Item |  |  | Reschedule a booking online |  |  | Contoso Field Service\Portal Team | Contoso Field Service |  |  | When my plans change, I want to reschedule my booking online so that I don't have to call the service desk. | • Customer can pick a new available slot for an open booking • Old slot is released • Updated confirmation shown with the same job ID
NEW |  | Task |  |  |  | Build reschedule slot picker |  | Contoso Field Service\Portal Team | Contoso Field Service |  |  | Build the slot picker for existing bookings so that customers can choose a new time.
NEW |  | Task |  |  |  | Release old slot on reschedule |  | Contoso Field Service\Portal Team | Contoso Field Service |  |  | Release the original slot in the scheduling system so that it can be booked by others.
NEW |  | Bug |  |  | Booking summary shows time in UTC |  |  | Contoso Field Service\Portal Team | Contoso Field Service |  | Defect | Fix the booking summary time zone so that customers see their local time (AEST). | • Summary shows the booked time in the customer's local time zone | • Book a job for 9:00 am • Open the booking summary • Time shows 11:00 pm (UTC)
CONTEXT | 1009 | Feature |  | Track job status |  |  | New | Contoso Field Service\Portal Team | Contoso Field Service |  | Portal | When I have a booked job, I want to see its status so that I know when the technician will arrive. | • Status visible for all open jobs
UPDATED | 1011 | Product Backlog Item |  |  | Text customer when technician is en route |  | New | Contoso Field Service\Portal Team | Contoso Field Service |  |  | When my technician is on the way, I want an SMS with their ETA so that I can be home when they arrive. | • SMS sent when the job status changes to En route • SMS includes technician first name and ETA |  | 13/10/2026 stand-up: Priya clarified scope – SMS on 'en route' with ETA. Title, description and AC updated.
CONTEXT | 1020 | Epic | Modernise the data platform |  |  |  | In Progress | Contoso Field Service\Platform Team | Contoso Field Service |  | Platform | Migrate the on-prem SQL Server to Azure SQL so that we reduce hosting cost and improve resilience. | • All portal data served from Azure SQL • On-prem server decommissioned
CONTEXT | 1021 | Feature |  | Migrate database to Azure SQL |  |  | In Progress | Contoso Field Service\Platform Team | Contoso Field Service |  | Platform | Migrate the portal database to Azure SQL so that the portal runs on managed infrastructure. | • Schema and data migrated with zero data loss • Portal cut over with under 1 hour downtime
REMOVED | 1025 | Product Backlog Item |  |  | Decommission on-prem database server |  | Removed | Contoso Field Service\Platform Team | Contoso Field Service |  |  | Decommission the on-prem SQL server so that hosting costs stop. | • Server powered off • Backups archived |  | Removed 13/10/2026: infra board decided the on-prem SQL server stays this FY for finance reporting. Re-raise next FY if needed.
NEW |  | Risk |  |  | Azure SQL cost exceeds FY budget |  |  | Contoso Field Service\Platform Team | Contoso Field Service |  |  | Reduce Azure SQL tier cost so that the migration stays within the FY budget. Estimate for Business Critical is ~40% over.
NEW |  | Feature |  | Export job data to finance warehouse |  |  |  | Contoso Field Service\Platform Team | Contoso Field Service |  |  | Export job data nightly to the finance reporting warehouse so that finance reporting keeps working after cut-over. | • Nightly extract of job data lands in the finance warehouse • Failed extracts alert the platform team
UPDATED | 1030 | Impediment | Test environment unavailable |  |  |  | Closed | Contoso Field Service | Contoso Field Service\Sprint 14 |  | Blocker | UAT environment is down after the network change so that testing can't proceed. |  |  | 13/10/2026 stand-up: UAT back up since Thursday – firewall rule fixed by network team.

## Change log
# | Change | ID / Ref | Type | Title | Parent | Field | Old value | New value | History | Justification | Source
1 | UPDATED | 1003 | Product Backlog Item | Submit a job booking | 1002 | History only |  |  | 13/10/2026 stand-up: demo to business accepted. Reschedule requested as a separate PBI. Stays Committed until address validation is done. |  | demoed job booking to the business on Friday
2 | UPDATED | 1004 | Task | Build booking form | 1003 | State | In Progress | Done | 13/10/2026 stand-up: booking form finished and merged (Liam). |  | booking form is finished and merged
3 | UPDATED | 1005 | Task | Validate address via address API | 1003 | State | To Do | In Progress | 13/10/2026 stand-up: address validation started. Blocked on vendor API key – see new impediment. |  | Started on address validation this morning
4 | NEW | N1 | Impediment | Obtain address API key from vendor | 1003 - Submit a job booking | (new item) |  | Obtain the address API key from the vendor so that address validation can be built and tested. | Raised at 13/10/2026 stand-up. Aisha to chase vendor. | Blocks Task 1005. No existing impediment covers it. | still waiting on the address API key from the vendor
5 | NEW | N2 | Product Backlog Item | Reschedule a booking online | 1002 - Book a job online | (new item) |  | When my plans change, I want to reschedule my booking online so that I don't have to call the service desk. |  | Business asked for it at the 13/10 demo. Fits Feature 1002 (Book a job online) – no existing PBI covers changing a booking. | customers want to reschedule a booking without calling
6 | NEW | N3 | Task | Build reschedule slot picker | N2 - Reschedule a booking online | (new item) |  | Build the slot picker for existing bookings so that customers can choose a new time. |  | Breakdown of N2. | Needs a date/time change
7 | NEW | N4 | Task | Release old slot on reschedule | N2 - Reschedule a booking online | (new item) |  | Release the original slot in the scheduling system so that it can be booked by others. |  | Breakdown of N2. | a cancellation of the old slot
8 | NEW | N5 | Bug | Booking summary shows time in UTC | 1002 - Book a job online | (new item) |  | Fix the booking summary time zone so that customers see their local time (AEST). |  | Defect found in testing; belongs to Feature 1002 where the summary page sits. | booking summary page shows the time in UTC
9 | UPDATED | 1011 | Product Backlog Item | SMS notifications | 1009 | Title 3 | SMS notifications | Text customer when technician is en route | 13/10/2026 stand-up: Priya clarified scope – SMS on 'en route' with ETA. Title, description and AC updated. |  | it's specifically 'text the customer when the technician is on the way', with ETA
10 | UPDATED | 1011 | Product Backlog Item | SMS notifications | 1009 | Description |  | When my technician is on the way, I want an SMS with their ETA so that I can be home when they arrive. | 13/10/2026 stand-up: Priya clarified scope – SMS on 'en route' with ETA. Title, description and AC updated. |  | it's specifically 'text the customer when the technician is on the way', with ETA
11 | UPDATED | 1011 | Product Backlog Item | SMS notifications | 1009 | Acceptance Criteria |  | • SMS sent when the job status changes to En route • SMS includes technician first name and ETA | 13/10/2026 stand-up: Priya clarified scope – SMS on 'en route' with ETA. Title, description and AC updated. |  | it's specifically 'text the customer when the technician is on the way', with ETA
12 | REMOVED | 1025 | Product Backlog Item | Decommission on-prem database server | 1021 | State | New | Removed | Removed 13/10/2026: infra board decided the on-prem SQL server stays this FY for finance reporting. Re-raise next FY if needed. |  | on-prem SQL server stays for the finance reporting workload this FY
13 | NEW | N6 | Risk | Azure SQL cost exceeds FY budget | 1021 - Migrate database to Azure SQL | (new item) |  | Reduce Azure SQL tier cost so that the migration stays within the FY budget. Estimate for Business Critical is ~40% over. |  | New risk raised by Sam. Directly affects Feature 1021. | Cost estimate ... came back ~40% over budget
14 | NEW | N7 | Feature | Export job data to finance warehouse | 1020 - Modernise the data platform | (new item) |  | Export job data nightly to the finance reporting warehouse so that finance reporting keeps working after cut-over. |  | No existing Feature covers reporting extracts. Sits under Epic 1020 because it is a direct consequence of the database migration. | finance needs a nightly extract of job data into their reporting warehouse
15 | UPDATED | 1030 | Impediment | Test environment unavailable | (top level) | State | Open | Closed | 13/10/2026 stand-up: UAT back up since Thursday – firewall rule fixed by network team. |  | UAT environment back up since Thursday

## Legend
Contoso Field Service - DevOps import preview
Source | Portal & Platform stand-up 13/10/2026
Generated | 2026-10-13
CSV file(s) | sample_devops_import.csv
Colour | Meaning
NEW (7) | New work item. Imports in its initial state (New / To Do / Open / Proposed).
UPDATED (5) | Existing item changed. Orange cells are the changed fields; History adds a Discussion comment.
Changed cell | The field value that will change on import.
REMOVED (1) | Existing item set to its Removed/Closed state. Never deleted. Reason recorded in History.
CONTEXT (5) | Unchanged parent row. Carries the hierarchy (Title 1/2/3...) so new children link to the right parent.
Import steps
Step 1 | Azure DevOps > Boards > Queries > Import work items > choose the CSV > Import.
Step 2 | Check the results grid: changed items show in bold, errors in red. Fix any red rows before saving.
Step 3 | Select Save items.
Step 4 | New items always import as New. To set another state, export them, change State and re-import.
Step 5 | Parent links come from Title column indentation. Context rows must stay in the file.